## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
sprint 1 | sprint 1 |  | Collect 15 research papers for the dataset | MUST HAVE | Research Sources | Sudarshan | 3- Completed
sprint 1 | sprint 1 |  | Extract abstracts and store in Word format | MUST HAVE | Python Scripts | Sudarshan | 3- Completed
sprint 1 | sprint 1 |  | Extract metadata, citations, and references and store in excel | MUST HAVE | Data Processing | Sudarshan | 3- Completed
sprint 1 | sprint 1 |  | Convert collected data into JSON format for ingestion | MUST HAVE | JSON Processing | Sudarshan | 3- Completed
sprint 2 | sprint 2 |  | Perform entity extraction from research paper data | MUST HAVE | NLP Model | Sudarshan | 3- Completed
sprint 2 | sprint 2 |  | Extract relationships between entities | MUST HAVE | NLP Model | Sudarshan | 3- Completed
sprint 2 | sprint 2 |  | Generate triples (subject–predicate–object) for knowledge graph | MUST HAVE | Data Structuring | Sudarshan | 3- Completed
sprint 2 | sprint 2 |  | Store triples in Neo4j database to build knowledge graph | MUST HAVE | Neo4j | Sudarshan | 3- Completed
sprint 3 | sprint 3 |  | Perform document chunking on research papers | MUST HAVE | LangChain | Sudarshan | 3- Completed
sprint 3 | sprint 3 |  | Generate embeddings for document chunks | MUST HAVE | Embedding Model | Sudarshan | 3- Completed
sprint 3 | sprint 3 |  | Store embeddings in FAISS vector database | MUST HAVE | FAISS | Sudarshan | 3- Completed
sprint 3 | sprint 3 |  | Implement RAG pipeline using LLM, FAISS, and knowledge graph | MUST HAVE | LLM + LangChain | Sudarshan | 3- Completed
sprint 4 | sprint 4 |  | Implement question answering system for research papers | MUST HAVE | RAG Pipeline | Sudarshan | 3- Completed
sprint 4 | sprint 4 |  | Evaluate responses using confidence and faithfulness metrics | MUST HAVE | Evaluation Module | Sudarshan | 3- Completed
sprint 4 | sprint 4 |  | Develop user interface to display summary and Q&A results | MUST HAVE | Streamlit UI | Sudarshan | 3- Completed
Note on F1: ====== ID#AAAB0z18xdc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Milestone 1 |  | Collect 15 research papers, extract abstracts, metadata, citations, and convert data into JSON format for ingestion | 2026-01-19 | 2026-01-30 | 1 | Research | 3- Completed | 8
Milestone 2 |  | Perform entity extraction, relationship extraction, and generate triples to build a knowledge graph in Neo4j | 2026-02-02 | 2026-02-11 | 1 | Coding | 3- Completed | 8
milestone 3 |  | Implement chunking, embedding, and FAISS vector database and integrate with LLM to build RAG pipeline with evaluation metrics | 2026-02-12 | 2026-02-20 | 1 | Coding | 3- Completed | 8
Milestone 4 |  | Develop and integrate user interface to display paper summaries, question answering, confidence, and faithfulness metrics | 2026-02-23 | 2026-03-04 | 1 | Design | 3- Completed | 8
Note on D2: ====== ID#AAAB0z18xdA Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB0z18xdE Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAB0z18xdg Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAB0z18xdw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAB0z18xd4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAB0z18xds Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAB0z18xdo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB0z18xdQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB0z18xdk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB0z18xd0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB0z18xdY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB0z18xeA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB0z18xd8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB0z18xdM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB0z18xc8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB0z18xdU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB0z18xdI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2026-12-29 | Introduction of project | understanding
1 | 2026-12-30 | algorithm working types | learning
1 | 2026-01-05 | understanding of GitHub | learning
1 | 2026-01-07 | basics of LLM | learning
1 | 2026-01-09 | LLM models | learning
1 | 2026-01-12 | transformer Function | learning
1 | 2026-01-14 | Lang chain crash course | learning
1 | 2026-01-20 | collections of data research papers | Data collection
1 | 2026-01-21 | collections of data research papers - Abstracts, reference list | Data collection
1 | 2026-01-23 | collections of data research paper - Metadata, Citation | Data collection
1 | 2026-01-27 | Convert collected data into JSON format for ingestion | Coding
1 | 2026-01-28 | Convert collected data into JSON format for ingestion | Coding
1 | 2026-01-30 | Presentation of milestone 1
2 | 2026-02-02 | Perform entity extraction from research paper data | NLP
2 | 2026-02-03 | Extract relationships between entities | NLP
2 | 2026-02-04 | Generate triples (subject–predicate–object) for knowledge graph | Data structure
2 | 2026-02-06 | Store triples in Neo4j database to build knowledge graph | Neo4j
2 | 2026-02-10 | Presentation of milestone 2
2 | 2026-02-11 | Presentation of milestone 2
3 | 2026-02-12 | Perform document chunking on research papers | Langchain
3 | 2026-02-13 | Generate embeddings for document chunks | Embedding Model
3 | 2026-02-16 | Store embeddings in FAISS vector database | FAISS
3 | 2026-02-17 | Implement RAG pipeline using LLM, FAISS, and knowledge graph | LLM + Langchain
3 | 2026-02-18 | Presentation of milestone 3
3 | 2026-02-19 | Presentation of milestone 3
3 | 2026-02-20 | Presentation of milestone 3
4 | 2026-02-23 | Implement question answering system for research papers | developing UI
4 | 2026-02-24 | Evaluate responses using confidence and faithfulness metrics | developing UI
4 | 2026-02-25 | Develop user interface to display summary and Q&A results | developing UI
4 | 2026-02-26 | Presentation of milestone 4
4 | 2026-02-27 | Mock Presentation
4 | 2026-03-02 | Presentation of milestone 4
4 | 2026-03-04 | Final presentation demo

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | sprint 1 | 2026-01-19 | 2026-01-30 |  | Better data organization | Manual formatting | Structured data collection | Created JSON pipeline
2 | sprint 2 | 2026-02-02 | 2026-02-11 |  | Improve entity extraction | Incorrect relationship mapping | Knowledge graph development | Optimized triple creation
3 | sprint 3 | 2026-02-12 | 2026-02-20 |  | Improve embedding quality | Large chunk sizes | Vector database usage | Optimized FAISS
4 | sprint 4 | 2026-02-23 | 2026-03-04 |  | Improve UI interaction | Complex UI layouts | User-friendly dashboard | Implemented final UI