## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sudarshan | 2026-01-27 | Incorrect JSON formatting during research paper data ingestion | Sprint 1 | Sudarshan | Logical | Fixed JSON conversion script and validated data structure | 2026-01-28 | Closed | Issue resolved after preprocessing
2 | Sudarshan | 2026-02-02 | Some entities not extracted correctly from research paper text | Sprint 2 | Sudarshan | Logical | Updated entity extraction rules and improved parsing | 2026-02-03 | Closed | Extraction accuracy improved
3 | Sudarshan | 2026-02-12 | Code structure difficult to maintain due to long functions | Sprint 3 | Sudarshan | Maintainability | Refactored code into modular functions | 2026-02-13 | Closed | Code readability improved
4 | Sudarshan | 2026-02-13 | Naming conventions not following project standards | Sprint 3 | Sudarshan | Standards | Updated variable and function naming conventions | 2026-02-14 | Closed | Coding standards applied
5 | Sudarshan | 2026-02-17 | FAISS retrieval occasionally returning less relevant chunks | Sprint 3 | Sudarshan | Standards | Optimized chunk size and embedding configuration | 2026-02-17 | Closed | Retrieval performance improved
6 | Sudarshan | 2026-02-25 | UI layout misalignment in summary display section | Sprint 4 | Sudarshan | User Interface | Adjusted Streamlit layout and styling | 2026-02-25 | Closed | UI display corrected

## Sheet2
Logical
User Interface
Maintainability
Standards
Others